## Sheet1
| Days | 0 | 1 | 2 | 3 | 4 | 5
| Actual Burndown | 45.5 | 43.5 | 29.8 | 19.75 | 13.59 | 6.59
| Ideal Burndown | 45.5 | 36.4 | 27.3 | 18.2 | 9.1 | 0
Task | Estimated Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Completed
Update MSQI Chart | 2 | 0 | 0 | 0 | 1 | 0 | y
Basement Room D: Assets & Props | 4 | 0 | 0 | 0 | 0 | 0
Basement Room B: Assets & Props | 1.5 | 0 | 2 | 0 | 0 | 0 | y
Basement Room C: Assets & Props | 1 | 1 | 1 | 0 | 0 | 0 | y
Basement Room E: Assets & Props | 2.5 | 0 | 1.5 | 0 | 0 | 0 | y
Basement Room F: Assets & Props | 3 | 0 | 0 | 2 | 3 | 2 | y
Room Allocation System | 6 | 0 | 4 | 1 | 0 | 0 | y
AI Patrolling | 8 | 0 | 0 | 3 | 2 | 4
Basement Room A: Event | 4 | 1 | 4 | 0 | 0 | 0 | y
Basement Room B: Event | 2 | 0 | 1 | 0 | 0 | 0 | y
Basement Room D: Event | 0.5 | 0 | 0 | 0 | 0 | 0
Basement Room E: Event | 4 | 0 | 0 | 0 | 0 | 0
Basement Room F: Event | 4 | 0 | 0 | 4 | 0 | 0 | y
Interaction Diagram (Final Event) | 1 | 0 | 0 | 0 | 0.16 | 0 | y
User Stories (Final Event) | 2 | 0 | 0.2 | 0.05 | 0 | 1 | y
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 |  | Velocity
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0