## Plan
| Goal of Sprint | Sprint Length | Any Waterfall Backlog Tasks | Any Sprint Backlog Tasks | New Tasks for Sprint
Sprint #1 | Implement Basement Props & Assets | 1 Week | Update MSQI Chart | N/A | Basement Landing: Assets & Props
Basement Room A: Assets & Props
Basement Room B: Assets & Props
Basement Room C: Assets & Props
Basement Room D: Assets & Props
Basement Room E: Assets & Props
Basement Room F: Assets & Props
Basement Layout In Product
Burndown Chart Template
Sprint #2 | Implement Final Event & Basement Events | 1 Week | Update MSQI Chart | Basement Room D: Assets & Props | Room Allocation System
|  |  |  | Basement Room B: Assets & Props | AI Patrolling
|  |  |  | Basement Room C: Assets & Props | Basement Room A: Event
|  |  |  | Basement Room E: Assets & Props | Basement Room B: Event
|  |  |  | Basement Room F: Assets & Props | Basement Room D: Event
Basement Room E: Event
Basement Room F: Event
Interaction Diagram (Final Event)
User Stories (Final Event)
Sprint #3 | Implement Essential Upper Floor Rooms | 1 Week | Update MSQI Chart | Basement Room D: Assets & Props | Door Locked UI
|  |  | Upper Floor Upper Foyer | Basement Landing: Assets & Props | Items
|  |  | Upper Floor Room D | AI Patrolling | Main Menu (Outside)
|  |  | Upper Floor Room F | User Stories (cont.) | Gamepad Input
|  |  | Upper Floor Room I |  | Fix Dialogue
Sprint #4 | Catchup on work so Final event can be started | 1 Week | Update MSQI Chart | User Stories (cont.) | Fix Lighting
|  |  | Upper Floor Upper Foyer | Door Locked UI | Implement Policeman
|  |  | Upper Floor Room D | Gamepad Input | Add Oujia Board
|  |  |  | Basement Room D: Assets & Props | Nav mesh Area's
|  |  |  | Basement Landing: Assets & Props | Save Game Script
Upper Floor Room I
Sprint #5 |  |  | Update MSQI Chart | Gamepad Input | Witch Model
|  |  | Upper Floor Room I Event | Door Locked UI | Cat Model
|  |  | Upper Floor Upper Foyer Event | User Stories (cont.) | Press Kit
|  |  |  | Fix Lighting | PP Presentation
|  |  |  | Save Game Script | Acceptance Testing
Analysis of 2nd Letter
Analysis of Final Event

## Retrospective
| What went well? | What could be improved? | What will we commit to improve in the next sprint?
Sprint #1 | All members got assets for the rooms within the sprint and began implementing them. All meetings were run with atleast 3 members present & the team as a whole got a fair bit done in the alloted time | All members could attend all meetings, members could ensure they get their work done by the end of the sprint. | Tasks estimated will be checked over by members and members will do their best to complete tasks on time for the end of the sprint.
Sprint #2 | Members who were able to work on their tasks managed to get the majority if not all their work doe within in the sprint | All members can do their best to communicate when unable to do work so others may make up the difference before the sprint finishes. | Task estimates will be done with a points system to gauge the best estimates for each task. The team's velocity will also be determined next sprint.
Sprint #3 | Not much really, team motivation was down due to the repetitive nature of the project | members could try to find some more motivation towards the project as there is only 3 more sprints to go | the group will try to finish up older tasks in the next sprint, delaying the final event to sprint 5
Sprint #4 | The team managed to get under the ideal burndown for the first few days in this sprint | members are still rather demotivated on the project, which is to be expected at this late stage | the group needs to just make sure the essential work gets done, the aim of the next two sprints is to achieve that
Sprint #5 | The team got the testing plan made and began testing each room | motivation was at an all time low. This is likely due to the projects overall scope and the amount of time we had left making people feel burned out. Considering the project was started 12 weeks ago it makes sense, considering how much needs doing. | As this was a last sprint, there isn't much to put here, but if we were to have another sprint we would try to improve team motivation and work on little bits at a time to finish to project