## Plan
| Goal of Sprint | Sprint Length | Any Waterfall Backlog Tasks | Any Sprint Backlog Tasks | New Tasks for Sprint
Sprint #1 | Implement Basement Props & Assets | 1 Week | Update MSQI Chart | N/A | Basement Landing: Assets & Props
Basement Room A: Assets & Props
Basement Room B: Assets & Props
Basement Room C: Assets & Props
Basement Room D: Assets & Props
Basement Room E: Assets & Props
Basement Room F: Assets & Props
Basement Layout In Product
Burndown Chart Template
Sprint #2 | Implement Final Event & Basement Events | 1 Week | Update MSQI Chart | Basement Room D: Assets & Props | Room Allocation System
|  |  |  | Basement Room B: Assets & Props | AI Patrolling
|  |  |  | Basement Room C: Assets & Props | Basement Room A: Event
|  |  |  | Basement Room E: Assets & Props | Basement Room B: Event
|  |  |  | Basement Room F: Assets & Props | Basement Room D: Event
Basement Room E: Event
Basement Room F: Event
Interaction Diagram (Final Event)
User Stories (Final Event)
Sprint #3 | Implement Essential Upper Floor Rooms | 1 Week | Update MSQI Chart | Basement Room D: Assets & Props | Door Locked UI
|  |  | Upper Floor Upper Foyer | Basement Landing: Assets & Props | Items
|  |  | Upper Floor Room D | AI Patrolling | Main Menu (Outside)
|  |  | Upper Floor Room F | User Stories (cont.) | Gamepad Input
|  |  | Upper Floor Room I |  | Fix Dialogue
Sprinty #4 | Catchup on work so Final event can be started | 1 Week | Update MSQI Chart | User Stories (cont.) | Fix Lighting
|  |  | Upper Floor Upper Foyer | Door Locked UI | Implement Policeman
|  |  | Upper Floor Room D | Gamepad Input | Add Oujia Board
Fix Dialogue

## Retrospective
| What went well? | What could be improved? | What will we commit to improve in the next sprint?
Sprint #1 | All members got assets for the rooms within the sprint and began implementing them. All meetings were run with atleast 3 members present & the team as a whole got a fair bit done in the alloted time | All members could attend all meetings, members could ensure they get their work done by the end of the sprint. | Tasks estimated will be checked over by members and members will do their best to complete tasks on time for the end of the sprint.
Sprint #2 | Members who were able to work on their tasks managed to get the majority if not all their work doe within in the sprint | All members can do their best to communicate when unable to do work so others may make up the difference before the sprint finishes. | Task estimates will be done with a points system to gauge the best estimates for each task. The team's velocity will also be determined next sprint.
Sprint #3 | Not much really, team motivation was down due to the repetitive nature of the project | members could try to find some more motivation towards the project as there is only 3 more sprints to go | the group will try to finish up older tasks in the next sprint, delaying the final event to sprint 5
Sprinty #4