## Sheet1
Risk ID | Identified Risk | Risk Target | Risk Probability | Risk Type | Qualitative Impact | Quantitative Impact | Prevention | Contingency Plan | Ed: Master | Ollie: Support
1 | Ed falls behind on work | Ed | Medium | Project | Major | Entire project | Weekly team meetings and assist member when needed | Hold meetups in uni where work must be done
2 | Sam falls behind on work | Sam | Medium | Project | Major | Entire project | Weekly team meetings and assist member when needed | Hold meetups in uni where work must be done
3 | Ollie falls behind on work | Ollie | Medium | Project | Major | Entire project | Weekly team meetings and assist member when needed | Hold meetups in uni where work must be done
4 | Jonathan falls behind on work | Jonathan | Medium | Project | Major | Entire project | Weekly team meetings and assist member when needed | Hold meetups in uni where work must be done
5 | Ed gets more external work hours | Ed | High | Project | Medium | 6 days | Contact work and notify them that you are unable to work extra hours. Or work around external work hours. | Hold meetups in uni where work must be done
6 | Sam gets more external work hours | Sam | High | Project | Medium | 6 days | Contact work and notify them that you are unable to work extra hours. Or work around external work hours. | Hold meetups in uni where work must be done
7 | Ed falls ill | Ed | Low | Health | Minor | 3 days | Wrap up warm use common sense when trying to prevent illness | Assist them where needed and allow for them to be able to get back up to speed as quickly as possible
8 | Sam falls ill | Sam | Medium | Health | Major | Min 7 days to a few weeks | No prevention, not predicatble (Long term illness) | Assist them where needed and allow for them to be able to get back up to speed as quickly as possible
9 | Ollie falls ill | Ollie | Low | Health | Minor | 3 days | Wrap up warm use common sense when trying to prevent illness | Assist them where needed and allow for them to be able to get back up to speed as quickly as possible
10 | Jonathan falls ill | Jonathan | Low | Health | Minor | 3 days | Wrap up warm use common sense when trying to prevent illness | Assist them where needed and allow for them to be able to get back up to speed as quickly as possible
11 | Ed doesnt turn up for meetings | Ed | High | Planning/Prep | Medium | 1 day | Set allarms, go to bed at a resonable time | Have meeting without and update at later time
12 | Sam doesnt turn up for meetings | Sam | Medium | Planning/Prep | Medium | 1 day | Set allarms, go to bed at a resonable time | Have meeting without and update at later time
13 | Jonathan doesnt turn up for meetings | Jonathan | Low | Planning/Prep | Medium | 1 day | Set allarms, go to bed at a resonable time | Have meeting without and update at later time
14 | Ollie doesnt turn up for meetings | Ollie | Low | Planning/Prep | Medium | 1 day | Set allarms, go to bed at a resonable time | Have meeting without and update at later time
15 | Github is Down | All | Low | Project | Major | 1-7 days | Make backups of projects so we can work on un event of shutdown | Work from backups
16 | HacknPlan is Down | All | Low | Project/Planning | Minor | 1-2 days | Write Individual check lists | Work from checklist
17 | Extreme Weather | All | Low | Project | Medium | 1-7 days | Check weather, dress for the weather | Try make your way into Uni if possible
18 | University Shutdown | All | Low | Project | Major | 1-7 days | Plan to meet/work elsewhere | Meeting a new place where it is possible to work from
19 | Kostas Ill | All | Low | Project | Major | 1-7 days | Make sure we as as team are up to date but still have tasks to complete | Work on old tasks to imporve on them if no new tasks can be given
20 | Discord Down | All | Low | Comunication | Medium | 1 days | Have other comunication lines set up | Use email or phone to contact team members
21 | Email Down | All | Low | Comunication | Medium | 1 days | Have other comunication lines set up | Use Discord or phone to contact team members
22 | Solent Online Learning Down | All | Low | Comincation | Medium | 1 days | Aqquire Kostas' email/Discord to contact in case | Email/Discord Kostas about tasks if needed